## Feuil1
Projet : univeler_phu Serveur : univeler.visualstudio.com\DefaultCollection Requête : univeler_phu Team - Sprint 1 - Backlog Type de liste : Arborescence
ID | Title 1 | Title 2 | State | Assigned To | Remaining Work
21 | Dashboard |  | Done
22 |  | choix des rôles | Done | Harold
23 |  | Découpage travail | Done | Harold
24 |  | Création planning | Done | Harold
17 | Développement |  | Committed
18 |  | Création BDD | In Progress | Morgan Le Bihan
19 |  | popup | In Progress | Aurélien MERZEAU
20 |  | Connexion API réseau sociaux | In Progress | traoreabdel@hotmail.fr
25 |  | Inscription_connexion | In Progress | Morgan Le Bihan
26 |  | création des vues | To Do | Harold
12 | déploiement |  | Done
13 |  | Affichage map | Done | Aurélien MERZEAU
14 |  | affichage dynamique des marqueurs | Done | Morgan Le Bihan
15 |  | Création popup | Done | traoreabdel@hotmail.fr
16 |  | ajout références | Done | Harold
3 | mise en place |  | Committed
4 |  | installation visual studio 2013 web | Done | Aurélien MERZEAU
5 |  | installation visual studio 2013 web | Done | Harold
6 |  | installation visual studio 2013 web | Done | Morgan Le Bihan
7 |  | installation visual studio 2013 web | In Progress | traoreabdel@hotmail.fr
8 |  | creation projet | Done | Harold
9 |  | synchronisation | Done | Aurélien MERZEAU
10 |  | synchronisation | Done | Morgan Le Bihan
11 |  | synchronisation | In Progress | traoreabdel@hotmail.fr

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | Approved | Aurélien MERZEAU | Closed | Aurélien MERZEAU | Accepted | Aurélien MERZEAU | Done | Aurélien MERZEAU | Active | Aurélien MERZEAU | Active | Aurélien MERZEAU | Closed | Aurélien MERZEAU | Approved | Aurélien MERZEAU | Active | Aurélien MERZEAU | Active | Aurélien MERZEAU | Done | Aurélien MERZEAU | Closed | Aurélien MERZEAU | Approved | Aurélien MERZEAU | Bug | \ | \ | Approved | Aurélien MERZEAU
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_dd/MM/yyyy HH:mm | readOnlyTestRange_General | Committed | Harold | Requested | Harold | Closed | Harold | In Progress | Harold | Closed | Harold | Closed | Harold | Open | Harold | Committed | Harold | Inactive | Harold | Closed | Harold | In Progress | Harold | Design | Harold | Committed | Harold | Code Review Request | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_System.AreaPath | \Release 1 | Committed | Harold
|  |  |  | Done | Microsoft.VisualStudio.Services.TFS | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Code Review Request_System.State | Microsoft.VisualStudio.Services.TFS | Requested | Microsoft.VisualStudio.Services.TFS | New | Microsoft.VisualStudio.Services.TFS | Removed | Microsoft.VisualStudio.Services.TFS | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Feedback Response_System.State | Microsoft.VisualStudio.Services.TFS | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Impediment_System.State | Microsoft.VisualStudio.Services.TFS | Done | Microsoft.VisualStudio.Services.TFS | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Shared Parameter_System.State | Microsoft.VisualStudio.Services.TFS | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Shared Steps_System.State | Microsoft.VisualStudio.Services.TFS | Removed | Microsoft.VisualStudio.Services.TFS | Ready | Microsoft.VisualStudio.Services.TFS | Done | Microsoft.VisualStudio.Services.TFS | Code Review Response |  | \Release 1\Sprint 1 | Done | Microsoft.VisualStudio.Services.TFS
|  |  |  | New | Morgan Le Bihan |  | Morgan Le Bihan | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Code Review Response_System.State | Morgan Le Bihan | Removed | Morgan Le Bihan | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Feedback Request_System.State | Morgan Le Bihan |  | Morgan Le Bihan |  | Morgan Le Bihan | New | Morgan Le Bihan |  | Morgan Le Bihan |  | Morgan Le Bihan | To Do | Morgan Le Bihan | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Test Case_System.State | Morgan Le Bihan | New | Morgan Le Bihan | Feature |  | \Release 1\Sprint 2 | New | Morgan Le Bihan
|  |  |  | Removed | TeamFoundationService (TEAM FOUNDATION) |  | TeamFoundationService (TEAM FOUNDATION) |  | TeamFoundationService (TEAM FOUNDATION) | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Feature_System.State | TeamFoundationService (TEAM FOUNDATION) |  | TeamFoundationService (TEAM FOUNDATION) |  | TeamFoundationService (TEAM FOUNDATION) |  | TeamFoundationService (TEAM FOUNDATION) | Removed | TeamFoundationService (TEAM FOUNDATION) |  | TeamFoundationService (TEAM FOUNDATION) |  | TeamFoundationService (TEAM FOUNDATION) | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Task_System.State | TeamFoundationService (TEAM FOUNDATION) |  | TeamFoundationService (TEAM FOUNDATION) | Removed | TeamFoundationService (TEAM FOUNDATION) | Feedback Request |  | \Release 1\Sprint 3 | VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_D2-7E-26-8A-A5-13-83-63-1E-0B-49-4A-C5-36-56-E6-37-B9-7B-0C | TeamFoundationService (TEAM FOUNDATION)
|  |  |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Bug_System.State | traoreabdel@hotmail.fr |  | traoreabdel@hotmail.fr |  | traoreabdel@hotmail.fr |  | traoreabdel@hotmail.fr |  | traoreabdel@hotmail.fr |  | traoreabdel@hotmail.fr |  | traoreabdel@hotmail.fr | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Product Backlog Item_System.State | traoreabdel@hotmail.fr |  | traoreabdel@hotmail.fr |  | traoreabdel@hotmail.fr |  | traoreabdel@hotmail.fr |  | traoreabdel@hotmail.fr | Closed | traoreabdel@hotmail.fr | Feedback Response |  | \Release 1\Sprint 4 |  | traoreabdel@hotmail.fr
[5 empty] | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Bug_System.AssignedTo |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Code Review Request_System.AssignedTo |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Code Review Response_System.AssignedTo |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Feature_System.AssignedTo |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Feedback Request_System.AssignedTo |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Feedback Response_System.AssignedTo |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Impediment_System.AssignedTo |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Product Backlog Item_System.AssignedTo |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Shared Parameter_System.AssignedTo |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Shared Steps_System.AssignedTo |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Task_System.AssignedTo |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_Test Case_System.AssignedTo | Requested | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_System.AssignedTo | Impediment |  | \Release 1\Sprint 5 |  | VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_EB-34-0D-26-EE-0F-70-89-7A-6A-59-57-02-12-79-FE-82-FB-9E-BC
[28 empty] | Accepted |  | Product Backlog Item |  | \Release 1\Sprint 6
[28 empty] | In Progress |  | Shared Parameter |  | \Release 2
[28 empty] | Active |  | Shared Steps |  | \Release 3
[28 empty] | Open |  | Task |  | \Release 4
[28 empty] | Inactive |  | Test Case |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_System.IterationPath
[28 empty] | To Do |  | all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_System.WorkItemType
Design
Ready
all_VSTS_52dfb07e_fa98_48f3_9885_ae7c484bcc3e_System.State